EXECUTIVE PROJECT CHARTER # Enterprise DevSecOps Transformation Professional Services Implementation ¦ ABC Manufacturing Portfolio case study- fictional organization and simulated project data

| PROJECT SPONSOR VP, Engineering | PROJECT MANAGER Eniola Ake | DURATION 7 months | BUDGET CAD $1.8M |
| --- | --- | --- | --- |
| DELIVERY MODEL Hybrid Agile | CUSTOMER TYPE Enterprise | STATUS Charter Approved | VERSION 1.0 |

EXECUTIVE DECISION REQUEST Authorize initiation of the Enterprise DevSecOps Transformation, approve the CAD $1.8M funding envelope, and confirm the governance model and executive sponsorship outlined in this charter.

# 1. Executive Summary

NorthStar Manufacturing currently relies on fragmented source code, deployment, and security tools. The resulting delivery model creates inconsistent release practices, limited executive visibility, delayed security reviews, and avoidable operational risk. This project will implement a standardized enterprise DevSecOps platform and establish repeatable delivery practices across priority application teams.

The project will be delivered through a hybrid Agile model over seven months. The Professional Services team will coordinate discovery, solution design, platform configuration, migration, testing, training, deployment, hypercare, and transition to operations. Success will be measured through adoption, release reliability, security integration, delivery visibility, and stakeholder satisfaction.

## Project at a Glance

| Business Outcome | Standardized, secure software delivery | Target Users | 12 application teams / 180 users |
| --- | --- | --- | --- |
| Primary Platform | Enterprise DevSecOps platform | Go-Live Target | Month 6 |
| Deployment Scope | Priority repositories and pipelines | Methodology | Hybrid Agile |
| Funding | CAD $1.8M | Executive Cadence | Monthly steering committee |
| Overall Risk | Medium | Change Control | Formal CCB |
| Hypercare | 4 weeks | Benefits Review | 90 days post-launch |

# 2. Purpose and Business Objectives

| OBJECTIVE | EXECUTIVE INTENT |
| --- | --- |
| Standardize delivery | Create consistent source-control, CI/CD, approval, and deployment practices across priority teams. |
| Strengthen security | Embed automated security checks earlier in the development lifecycle. |
| Improve visibility | Provide leaders with reliable portfolio, release, risk, and delivery metrics. |
| Reduce delivery friction | Remove duplicate tools, manual handoffs, and unclear ownership. |
| Enable adoption | Train technical teams and establish sustainable operating procedures. |

# 3. Scope

| IN SCOPE | OUT OF SCOPE |
| --- | --- |
| • Current-state assessment and detailed planning | • Enterprise-wide migration of all legacy applications |
| • Platform configuration and access model | • Replacement of unrelated business applications |
| • Migration of priority repositories and pipelines | • Major application code remediation |
| • Security scanning and approval workflow integration | • 24/7 managed support after hypercare |
| • SIT, UAT, cutover, training, and hypercare | • Organization-wide operating model redesign |
| • Operational handover and project closure | • Procurement outside the approved funding envelope |

# 4. Delivery Approach and Major Milestones

| PHASE | WORKSTREAM | TIMING | EXIT OUTCOME |
| --- | --- | --- | --- |
| 1 | Discovery & Initiation | Weeks 1–4 | Current-state assessment, charter, governance, backlog |
| 2 | Design & Planning | Weeks 5–8 | Solution design, migration waves, integrated schedule |
| 3 | Configure & Pilot | Weeks 9–16 | Platform configuration, pilot repositories, controls |
| 4 | Migration & Validation | Weeks 17–22 | Repository migration, SIT/UAT, training readiness |
| 5 | Go-Live & Hypercare | Weeks 23–28 | Cutover, stabilization, handover, closure |

# 5. Governance and Decision Rights

| ROLE | DECISION ACCOUNTABILITY |
| --- | --- |
| Executive Sponsor | Owns business outcome, funding, executive escalations, and final decisions. |
| Steering Committee | Reviews project health, approves major scope/budget decisions, removes barriers. |
| Project Manager | Owns integrated delivery, governance, schedule, budget, RAID, reporting, and customer expectations. |
| Technical Architect | Owns solution integrity, technical decisions, and design assurance. |
| Workstream Leads | Own detailed execution, estimates, dependencies, quality, and timely status updates. |
| Change Control Board | Assesses change impacts and approves or rejects baseline changes. |

# 6. Financial and Commercial Controls

| APPROVED FUNDING ENVELOPE | CAD $1.8M | FORECAST TOLERANCE | ±5% before mandatory executive review |
| --- | --- | --- | --- |
| CHANGE ORDERS | Required for approved work outside baseline scope | REVENUE SUPPORT | Monthly milestone and effort validation |
| INVOICE READINESS | Validated against accepted deliverables and contractual terms | CONTINGENCY | 10% included within the approved budget |

# 7. Key Risks and Executive Responses

| ID | RISK | RATING | RESPONSE |
| --- | --- | --- | --- |
| R1 | Migration complexity | High | Pilot first; wave-based migration; rollback criteria. |
| R2 | Resource contention | High | Named capacity commitments; escalation within 48 hours. |
| R3 | Adoption resistance | Medium | Role-based training, champions, office hours, and adoption metrics. |
| R4 | Security/control gaps | High | Security design review and mandatory quality gates. |
| R5 | Scope growth | Medium | Formal change control and impact-based approval. |
| R6 | Dependency delays | Medium | Integrated dependency log and weekly cross-team review. |

# 8. Success Measures and Acceptance Criteria

| MEASURE | TARGET / ACCEPTANCE THRESHOLD |
| --- | --- |
| Platform adoption | At least 85% of target users are active within 60 days |
| Migration completion | 100% of approved pilot and wave repositories migrated |
| Release reliability | At least 30% reduction in failed or rolled-back releases |
| Security integration | Automated security checks are enabled for all migrated pipelines |
| Executive visibility | Monthly dashboard delivered with agreed metrics and data quality |
| Stakeholder confidence | Average sponsor and customer satisfaction of 4.2/5 or higher |
| Operational readiness | Support model, runbooks, ownership, and SLAs accepted before closure |
| Financial performance | Final forecast within ±5% of approved budget |

# 9. Assumptions and Constraints

| ASSUMPTIONS | CONSTRAINTS |
| --- | --- |
| • Customer SMEs are available for workshops and acceptance decisions. | • Seven-month delivery window. |
| • Technical environments and access are provisioned on schedule. | • CAD $1.8M approved funding limit. |
| • Required licenses and partner resources are available. | • Production changes must follow customer change windows. |
| • Executive sponsor resolves escalations promptly. | • Priority resources remain shared with business-as-usual work. |

# 10. Approval and Authorization

Approval confirms agreement with the project purpose, scope, funding envelope, governance model, success measures, and decision rights. Any material deviation will be managed through the approved change-control process.

| ROLE | NAME | SIGNATURE | DATE |
| --- | --- | --- | --- |
| Executive Sponsor | Jordan Lee |  |  |
| Customer Technology Leader | Avery Chen |  |  |
| Professional Services Director | Morgan Patel |  |  |